## Slide 1
ACG Electronics
Swimlane
(Common Development Process)
Revised: January 21, 2014

## Slide 2
Revised: January 21, 2014

## Slide 3
Revised: January 21, 2014

## Slide 4
Revised: January 21, 2014

## Slide 5
Revised: January 21, 2014

## Slide 6
Revised: January 21, 2014

## Slide 7
Revised: January 21, 2014

## Slide 8: EE Work Packages Summary
Assumptions – High Voltage EM Box with 90% Reuse, 6 Unique CCAs, DO-254 Level A design, Microprocessor and PLD, BLDC Motor design with reuse of magnetic design (pole/slot)
Notes: 8
Details of work packages (i.e. deliverables) are 40% available. Sources for deliverables:
Past programs (e.g. 787, F-35)
Brainstorm sessions ran by Rick Fosdick
ARP4754 is main guidance for assurance
Cross-check with CMMI and other disciplines
SE work packages do not include Box (LRUs, Software, anything below Allocations) deliverables
Version history
3/15/09 – added “Test Equipment Definition” work package, added “TSE: Test Systems and Equipment” team acronym, changed “Test Script Generation” from the red “IAT” to the green “TSE”, added “Test Equipment Build and Verification” work package, changed “SOF Testing” to “System SOF Testing” and changed the work package from red to orange, added “Box SOF and Qualification” work package, changed “Qual Test and Flight Test Support” to Flight Test Support”, added “System Qualification Testing” work package, added “Regression Testing” work package, added “Development and Qualification Labs” team acronym
8

## Slide 9: Phase 1 – Project Planning Work Package
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 10: Preliminary Design – Digital Work package
Proposal Baseline
Proposal volumes (inc DTC)
Contract Spec & SOW
Electrical Engineering Budget
Platform Baseline/Templates
Org Project Standards
Planning Document Templates
Program Plan
Customer schedule/milestones
Program organization chart
Work Authorization (WO #)
Planning
PHAC, HDP, HVP, SSMP, HPAP, HCMP,etc… (480)
Develop EE Risk Mitigation plan (32)
Create IP protection plan (24)
Plan for export compliance and licensing (24)
Manufacturing Concept Strategy(8)
Project Preparation
Create Integrated EE Schedule (44)
Create EE WBS and WP definition (40)
Update EE Program ETC (24)
Create Electrical IPT organization/plan (24)
Generate project data repository structure (18)
Design Requirements & Standards
Review deltas from proposal and award (24)
Review and update assumptions (28)
Define applicable design process std (32)
Kick-off
Identify IR&D / platform candidates and kick-off (30)
Other EE team support including trades (320)
Inputs
Tasks / ETC
Deliverables
Resources (1152 hrs)
- Primary: EE Project/IDVT (352)
Other EE teams (800)
Project Planning – IDVT WP1
1. Integrated EE Schedule / WBS / ETC – as required
2. Certification Planning Docs (E release):
PHAC, HDP, HVP, HCMP, HPAP,SSMP
3. SDRL list / schedule – as required
4. EMC Control Plan – as required (E release)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 11: Phase 1 Exit Criteria
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 12: Phase 2 – Requirements Definition Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 13: Requirement Development Work package
Requirement
Proposal volumes
Proposal HW assumptions
Proposal FW allocation assumptions
Customer Statement of Work
System Top Level Definition
Standards / Guidelines Platform FEs
Design process standards
Trades with other swimlanes
Trade Studies
Other EE teams support including trades (600)
Generate conceptual Box HDD (120)
Define Box / CCA Architecture/technical approach (120)
• Platform reuse and development Items
• Partitioning & associated trade studies
• Reliability and safety allocations
Item Definition
Generate preliminary Box block diagrams (80)
Generate Grounding Scheme (40)
Define Box Hardware Requirements
including derived requirements (240)
Generate Requirement trace matrix (120)
Create Product Structure Diag with PNs (28)
CCA Block Diagrams and HRDs (300, 300)
Baseline Requirements (16)
SRR Preparation (24)
Reviews/Project/Plans
Review requirements formally Int/Ext (48)
Requirements Peer Reviews (32)
EVMS Updates (32)
Create control plans - HV, EMC (100)
Collaborate Manufacturing Plan development (16)
Inputs
Tasks / ETC
Deliverables
Resources (2216 hrs)
Primary: IDVT/Proj (1316)
Other EE teams (900)
Requirements Definition – IDVT WP2
Box Block Diagram
  project file (part of HRD)
Grounding approach
  project file (part of HRD)
ICD
  project file (part of HRD)
LRU HRD
  (E release) - prelim baseline in Doors
CCA HRDs
  as required (E release) – in Doors
Drawing Tree
  MRE document (E release)
Checklists / guidelines / templates
  distribution
DFX goals
  project memo
9. Control Plans – HV, EMC
  project memo
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 14: Qual Test Work Package
Preliminary PLD/Firmware definition
Identify the FEs / logic to be implemented in PLD (80)
Generate PLD high level block diagram (40)
Generate IO List (20)
Perform high level Timing analysis (80)
Update Planning Docs (80)
Create FRD0 (120)
Inputs
Tasks / ETC
Deliverables
Resources (420 hours)
DDVT (420)
Requirements
Board Requirement – HRD
Plans
V&V plans
PHAC, HVP, HDP, HPAP, HCMP
Guidelines / Standards
Requirement & Coding standard Platform Functional Element –
VHDL core
1. PLD block diagram and IO List – project file
2. SOI 1 - audit results in clear case (as required)
3. FRD0 (DDVT activity) – E release
4. 5. Planning Doc’s Released (EO)
Requirement Development Work package
Requirements Definition – VnV (DDVT) WP3
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 15: Phase 2 Exit Criteria
Return to summary page
Return to swimlane
Phase 2 – Requirements Definition
☐Complete, ☐N/A: Box Block Diagram, project file (part of HRD)
☐Complete, ☐N/A: Grounding approach project file (part of HRD)
☐Complete, ☐N/A: ICD project file (part of HRD)
☐Complete, ☐N/A: LRU HRD (E release) - prelim baseline in Doors
☐Complete, ☐N/A: CCA HRDs as required (E release) – in Doors
☐Complete, ☐N/A: Drawing Tree MRE document (E release)
☐Complete, ☐N/A: Checklists / guidelines / templates distribution
☐Complete, ☐N/A: DFX goals project memo
☐Complete, ☐N/A: PLD block diagram and IO List – project file
☐Complete, ☐N/A: SOI 1 - audit results in clear case (as required)
☐Complete, ☐N/A: All Planning Doc’s EO Released
☐Complete, ☐N/A: FRD0 (DDVT activity) – E release
☐Complete, ☐N/A: Control Plans (HV, EMC) - project memo
Revised: January 21, 2014

## Slide 16: PH 3 – Preliminary Design Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 17
Coordinate:
Box Block diagram, area, power estimates (60)
Source Control Drawings for Sensors, etc (120)
DFMAT, DTC and Obsolescence report (60)
Preliminary Box layout - fit, thermal (60)
Prototype / Risk mitigation testing (80)
Preparation of Data Items (80)
Box Reliability / FMEA analysis (40)
Auditing of guidelines / checklist (40)
Box PDR package (120)
Box BOM creation (40)
Peer Review with EMC and Subject MEs (40)
Box Design trades (80)
Lead project activities (120)
Develop Box Verification Matrix (40)
Update Box HRD (60)
Dev test plan (60)
Generate Box Test equipment requirements (40)
Support System PDR and Box PDR (40)
Inputs
Tasks / ETC
Deliverables
Resources (1180 hours)
IDVT (1180)
Schedule
Program IMS & ETCs
Program data Item deliverables
Requirements
SRR actions
Updated Hardware Allocation
Box Requirement – HRD
HRD to CCA HRD RQMT Trace
Safety Requirements
Grounding approach
Plans
Manufacturing Plans EMCP1
V&V plans ( PHAC, HVP, HDP)
Risk mitigation plan
DFX
DTC targets and DFMAT plans
Guidelines
Guidelines / Checklists
Platform Functional Elements
Requirements - Box HRD update as required
  (E release) Doors REV
Requirements – Preliminary Compliance Matrix
  (with MOC defined) (E release)
Requirements - Box level requirements
  check list – clear case
Trade Study – if needed
  project memo
Peer Review documentation with SME
  project memo
Test Equipment req’t document
  project memo
DFMAT review with MFG
  project memo
PDR review package – as required
Qual Test Work Package
Requirement Development Work package
Preliminary Design – IDVT WP5
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 18: Qual Test Work Package
Design/Analysis
Generate Source Control Drawing as needed (40)
Generate Library models (60)
Generate Schematics (40, 60)
Generate BOM, DTC and Obsolescence report (60)
Perform PLD design activity (120)
Perform preliminary parts placement (80)
Perform Design Analysis / Sim – Stress, derating (80)
Update CCA HRD (80)
Reviews and other support
Prototype / Risk mitigation plan and testing (80/80)
Generate DFMAT compliance report (40)
Generate CCA Test equipment req’t document (40)
Support Reliability / FMEA analysis (20)
Capture design data in repository (40)
Support Peer Review with EMC and SMEs (40)
Prepare PDR package (80)
Inputs
Tasks / ETC
Deliverables
Resources (1040 hours)
- DDVT (700 hrs)
- Components (120 hrs )
PWB design (140 hrs)
EE Tech (80 hrs)
Preliminary Design – DDVT WP6
Requirements - CCA HRD update as required (E release) Doors REV
Requirements – Preliminary Compliance Matrix
  (with MOC defined) (E release)
Trade Study, if needed – project memo
Area, power estimates, if needed – project memo
FRD1 REV update
Schematic Preliminary
  Peer review with SME – project memo
Schematic Preliminary
  (E release – if needed for prototype)
BOM, (E release – if needed for prototype)
BOM - DTC compliance & Obsolescence summary
  project memo
ABOM – long lead items if needed
  project memo or spread sheet
PDR review package – as required
PDR DDVT checklists
Requirements
Box Requirements - HRD
CCA Requirement – HRD
Plans
DTC targets and DFMAT plans
Grounding Approach
Risk Mitigation Plan
Program IMS & ETCs
Guidelines
Platform Functional Elements
Guidelines & Checklists
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 19
Requirements
Box HRD
CCA HRD
Platform Functional Elements
Plans
DTC targets and DFMAT plans
Risk mitigation plan
V&V plans (PHAC, HVP, HDP)
Program IMS & ETCs
FRD0
Guidelines
Documentation requirements,
templates, checklists
Inputs
Tasks / ETC
Deliverables
Resources (360 hours)
- DDVT (360)
Requirement Reviews
Review released requirements (E-released) against check list (60)
Review preliminary test approach vs V&V plan (40)
Plans
Set Up V&V Data folders in Configuration Management System (40)
Analysis / Tracing / Procedures
Develop HVCP (60)
Identify required test cases
Identify required robustness testing
Estimate/allocate tool usage (40)
Work CCA tracing to PLD (80)
PDR review package, as required
Qual Test Work Package
Requirement Development Work package
Preliminary Design – FW V&V WP7
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 20: Qual Test Work Package
Design/Analysis
Perform Design trades (120)
Generate Schematics (100/60)
Generate CCA Block diagram, Area, power estimates (120)
Update CCA HRD (80)
Perform Design Analysis / simulation – Stress, derating (80)
Generate BOM, DTC and Obsolescence report (60)
Grounding Scheme (40)
Perform preliminary parts placement (80)
Generate Library models (60)
Generate Source Control Drawing as needed
Reviews and other support
Prototype / Risk mitigation plan and testing (80/80)
Generate DFMAT compliance summary (40)
Generate CCA Test equipment requirement (40)
Support Reliability / FMEA analysis (20)
Capture design data in repository (40)
Support Peer Review with EMC and SMEs (40)
Prepare PDR package (80)
Requirements
Box Requirements - HRD
CCA Requirement – HRD
Plans
DTC targets and DFMAT plans
Grounding Approach
Risk Mitigation Plan
Program IMS & ETCs
Guidelines
Platform Functional Elements
Guidelines & Checklists
Inputs
Tasks / ETC
Deliverables
Resources (1220 hours)
- ADVT (880 hrs)
- Components (120 hrs )
PWB design (140 hrs)
EE Tech (80 hrs)
Preliminary Design – ADVT WP8
Requirements - CCA HRD update
  as required (E release) Doors REV
Requirements – Prelim Compliance Matrix
  (with MOC defined) (E release)
Trade Study, if needed – project memo
Area, power estimates
  if needed – project memo
Schematic Preliminary
  Peer review with SME – project memo
Schematic Preliminary
  (E release – if needed for prototype)
BOM, (E release – if needed for prototype)
BOM - DTC compliance & Obsolescence
  Summary - project memo
ABOM – long lead items if needed
  project memo or spread sheet
PDR review package – as required
PDR ADVT checklists
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 21: Qual Test Work Package
Design/Analysis
Perform Design trades (120)
Generate CCA Block diagram, Area, power est (120)
Grounding Scheme (40)
Generate Source Control Drawing as needed
Magnetics Design (120)
Generate Library models (60)
Generate Schematics (100/60)
Generate BOM, DTC and Obsolescence report (60)
Perform preliminary parts placement (80)
Perform Design Analysis / sim – Stress, derating (80)
High Voltage Risk Identification (40)
Program High Voltage Guideline (20)
Update CCA HRD(80)
Generate CCA Test equipment requirements (40)
Reviews and other support
Prototype / Risk mitigation plan and testing (80/80)
Generate DFMAT compliance report (40)
Support Reliability / FMEA analysis (20)
Capture design data in repository (40)
Support Peer Review with EMC and SMEs (40)
Prepare PDR package (80)
Inputs
Tasks / ETC
Deliverables
Resources (1220 hours)
- PDVT (880 hrs)
- Components (120 hrs )
PWB design (140 hrs)
EE Tech (80 hrs)
Preliminary Design – PDVT WP9
Requirements - CCA HRD, update as required (E release) Doors REV
Requirements – Preliminary Compliance Matrix
  (with MOC defined) (E release)
Trade Study
  if needed – project memo
Area, power estimates
  if needed – project memo
Schematic Preliminary
  Peer review with SME – project memo
Schematic Preliminary
  (E release – if needed for prototype)
BOM
  (E release – if needed for prototype)
BOM - DTC compliance & Obsolescence summary
  project memo
ABOM – long lead items if needed
  project memo or spread sheet
High Voltage Guideline
PDR review package – as required
PDR PDVT checklists
Requirements
Box Requirements - HRD
CCA Requirement – HRD
Plans
DTC targets and DFMAT plans
Grounding Approach
Risk Mitigation Plan
Program IMS & ETCs
High Voltage Control Plan
Guidelines
Platform Functional Elements
Guidelines & Checklists
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 22
Requirements
Box HRD including envelope
Mission Profiles
Board Requirements – # and type of cards
Plans
High voltage control plan
Risk mitigation plan
Grounding approach
Program IMS & ETCs
Guidelines
Board BOM as available
Board Power / Area Estimates
Platform Functional Elements (info only)
DTC targets and DFMAT plans
Inputs
Tasks / ETC
Deliverables
Resources (740 hours)
PACT (740)
Design/Analysis
Perform Packaging Design trades (60)
Generate preliminary Box volume and weight estimates (60)
Generate Source Control Drawings (80)
Define Library models (connectors / or standard material) (40)
Generate BOM, DTC and Obsolescence report (connectors, screws,
long lead Items) (80)
Generate drawing tree (20)
Prepare preliminary 3D model (80)
Perform Preliminary Design Analysis / simulation –Thermal, Vibe,
fatigue, tolerance stack-up (120)
Generate DFMAT concept (20)
Support high voltage and separation rules (20)
Reviews and other support
Perform Peer Review with SMEs (40)
Prototype / Risk mitigation plan and testing (40)
Support Test equipment requirement doc for development testing (20)
Prepare PDR package (60)
Requirements – Box Level
  requirements check list – clear case
Trade Study – if needed Project Memo
BOM (E release – if needed for prototype)
ABOM – long lead items if needed
  project memo or spread sheet
Packaging - Preliminary 3D CAD model
  (no release)
Packaging - Preliminary board DXF to CAD
  (no release)
Packaging - Preliminary Assembly Drawing
  (E release)
Packaging - Peer Review with SME
project memo
9. Preliminary Design analysis / Simulation
- Thermal, Vib, Fatigue, Tolerance stack up
10. PDR review package – as required
11.PDR PACT checklists
Qual Test Work Package
Preliminary Design – PACT WP10
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 23
Design/Analysis
Cost, weight, envelope, performance trades (60)
Prelim. magnetic and performance analysis (140)
Prelim Assembly Design/ Modeling (50)
Prelim Stress Analysis (20)
Components supplier selection (10)
Components design/modeling (40/10)
Component drafting drawings (20/10)
Prototype Motor Design (80/80)
Reviews and other support
HV / Corona mitigation plan (10)
Plan and prepare for Prototype Motor Test from platform (40/80)
Prepare PDR package (60/20)
Requirements
Motor Platform
Torque-Speed-Power
Rtt/Ltt, Kt/Ke,
Inertia, peak acceleration
Min/Max Voltage/Current
Commutation/Sensor Type
Cable length, Environmental
DTC targets and DFMAT plans
Plans
Risk mitigation plan
Grounding approach
Program IMS & ETCs
Guidelines
DTC, DFMAT Requirements
Motor platform elements
1. Prelim. Top-level Assembly drawings – E released
2. Prelim. Motor Envelope
3. Prelim. Stator and Rotor Dims & weight
4. Prelim. Motor Design Data
5. Prelim Performance Analysis
6. Prelim Thermal analysis
7. Prelim. Stress analysis
8. Mechanical Components Design
9. Peer review Documentation (project)
10. Motor PDR package (project)
11. Prototype Motor BOM and detailed drawings as required (E release)
12. PDR MDVT checklists
Inputs
Tasks / ETC
Deliverables
Resources (730 hrs)
-Motor design (530 hrs)
Drafting (120 hrs)
Technician (80 hrs)
Preliminary Design – MDVT WP10
Return to summary page
Return to swimlane
Revised: January 21, 2014
Notes: 23

## Slide 24: Phase 3 Exit Criteria
Revised: January 21, 2014

## Slide 25: Phase 3 Exit Criteria
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 26: Phase 3 Exit Criteria
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 27: Phase 4 – Detail Design Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 28
Inputs
Tasks / ETC
Deliverables
Resources
IDVT (1544)
Project
Program IMS & ETCs
Program data Box deliverables
Trade Study Results
Plans
Supply Chain Plan
V&V plans ( PHAC, HVP, HDP)
DTC targets and DFMAT plans
Risk mitigation plan
HALT/HASS Plan
Updated Material Plan
Requirements
Updated Hardware Allocation
Updated Box Requirement – HRD
HRD to CCA HRD Reqt’s Trace
EMCP
Design trade study – if needed –
  project memo
Estimate - Area, power - if needed
  project memo
Block diagram (Box and Card)
  MRE document (EO release)
Requirement - Box HRD
  (EO release) REV Doors - clear case
Requirement - Pin Assignments (ICD / Box pins)
  spread sheet – project file
Requirement derived justification
  link in Doors – clear case
Requirement tracing and review check list
  clear case
CDR review package – as required
Project
Lead activities (60)
Finalize BOM and DTC (40)
Supply chain support (40)
DFMAT compliance report (40)
Support preparation of data items (80)
Complete box EMC control plan (80)
Requirements
Finalize Box Block Diagram (80)
Finalize Box requirements (160)
Finalize Test Equipment requirements (60)
Design Support / Reviews
Area and power estimates (40)
Ensure completion of Box layout, fit, Thermal, Weight (24)
Complete box verification matrix (160)
Perform peer reviews with EMC and SME’s (60)
Prepare box CDR package (80)
Support CDR (30)
Drawings
Box – top level drawing (30)
Source control drawings for Sensors (80)
Test
Complete prototype risk mitigation testing (160)
Dev test plans, ATP,SOF, Qual (240)
Detailed Design – IDVT WP13
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 29: Preliminary design – Digital Work package
Requirements
Box Requirement - HRD
CCA Req’t Document - HRD
Firmware Requirements - FRD
Preliminary Design Documentation
Preliminary design data & Documents
Risk mitigation test results
Plans
V&V plans ( PHAC, HVP, HDP)
DTC targets and DFMAT plans
Guidelines & Checklists
Program IMS & ETCs
Inputs
Tasks
Deliverables
Detailed Design – DDVT WP14
Resources :
- DDVT ( 2240 hrs)
- Components ( 120 hrs )
- PWB design ( 360 hrs)
- EE Tech ( 120 hrs)
Design trade study – if needed
  project memo
Estimate - Area, power if needed
  project memo
Block diagram (CCA)
  MRE document (EO release)
Requirement CCA card HRD – if needed
  (EO release) REV Doors – clear case
Requirement FRD2 REV, (EO release) – clear case
Schematic Peer Review
  project memo – results of review with SME
Schematic checklist data base in team center
  error report completed and resolved – team center
  E release until built – EO release prior to qual
Board layout guidelines for each CCA (EDP)
  team center
Board layout Peer Review, part place and trace routing checklist – project file
BOM - (E release – EO release prior to qual)
BOM - DTC compliance and Obsolescence report
  memo or spread sheet
Analysis (initial / final after qual) –
  Derating / signal integrity/ timing analysis
  project file / clear case
Test Procedure (E release)
CDR review package – as required
PLD Design – PLD source code
  Captured in Clear case
Requirement derived justification - link
in Doors clear case
17. CDR DDVT checklists
Requirements
Finalize block diagram (80)
Update CCA HRD and FRD (120)
Design
Finalize schematic (240)
Firmware design (360)
Test Benches (120)
Generate EDP (40)
Perform board layout / trace route (360)
Analysis
Finalize Design Analysis, Stress, Timing, Signal integrity (320)
Support Reliability / FMEA analysis (40)
Functional/post-route Simulation (160)
Generate requirement to design compliance matrix (160) Components
Finalize BOM, DTC and Obsolescence (80)
Generate library models as needed (40)
Test
Generate board test requirements (240)
Finalize prototype risk testing (120)
Reviews / Reports
Schematic, layout and tracing routing review (80)
Update DMFAT compliance report (40)
Prepare CDR package (60)
Generate SDRL documents (60)
Prepare design doc – HDD (160)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 30: Preliminary design – Digital Work package
Procedure/Test Bench
Generate HVTCP (320 hrs)
Generate/update Test Benches (320 hrs)
Analysis / Simulation
Initial Functional Simulation (320 hrs)
Identifying failures (if any) and analysis (40)
Timing simulation for Typ, Min, Max (320 hrs)
Reviews / Reports
HVCP Peer review & updates (120 hrs)
TB Peer review & updates (120 Hrs)
Generate HVR for simulations (120 hrs)
RQMT clarification based on simulation failure (80)
Hardware Verification Report / Analysis for
Simulation (160 hrs)
Problem Report / CR (80 hrs)
Requirement
Preliminary FRD
Plans
HVP
Preliminary HVCP
Standards
VHDL standards
Check lists (HVCP, TB, HVR)
Design / Models
DUT
Models
Inputs
Tasks
Deliverables
Resources :
DDVT (2000 hrs)
Detailed Design – PLD VnV WP15
Requirement derived justification Review - link
in Doors clear case
2.Requirement tracing and review check list
  clear case
3.PLD source code review checklist –
  Clear Case
4.PLD source code traceability –
  Clear Case
5.Functional test Benches
  Captured in Clear Case
6.Functional PLD and post route simulation
  results captured in project file
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 31: Preliminary design – Digital Work package
Requirements
Finalize CCA Block diagram, Area, power estimates (60)
Update CCA HRD (40)
Generate Requirement to Design Compliance Matrix (40)
Design
Finalize Schematics (120)
Generate Board layout guidelines (EDP) (60)
Finalize parts placement (80)
Perform Board Layout (240)
Analysis
Finalize Design Analysis / sim – Stress, derating, HV (40)
Support Reliability / FMEA analysis (20)
Components
Generate Library models as needed (20)
Finalize BOM and scrub for PPL (40)
DTC and Obsolescence report (40)
Test
Prototype / Risk mitigation plan and testing (80)
Generate Board Test Requirement for V&V (40)
Reviews / Reports
Update DFMAT compliance report (40)
Preliminary Board Design Document – HDD (60)
Perform Peer Review including EMI and SMEs (20)
Prepare CDR package (40)
Generate SDRL documents (40)
Requirements
Box Requirement - HRD
CCA Req’t Document - HRD
Preliminary Design Documents
Preliminary design data & doc’s
Risk mitigation test results
Plans
DTC targets and DFMAT plans
Guidelines & Checklists
Program IMS & ETCs
Inputs
Tasks
Deliverables
Resources :
- ADVT (620 hrs)
- Components ( 100 hrs )
- PWB design ( 320 hrs)
- EE Tech ( 80 hrs)
Detailed Design – ADVT WP16
Design trade study – if needed, project memo
Estimate - Area, power if needed, project memo
Block diagram (Card), MRE document (EO release)
Requirement CCA card HRD – if needed
  (EO release) REV Doors – clear case
Schematic Peer Review –
  project memo – results of review with SME
Schematic checklist
  error report completed and resolved – team center
Schematic
  (E release until built – EO release prior to qual)
  data base in team center
Board layout guidelines for each CCA
  (EDP) – team center
Board layout Peer Review, part placement and trace routing checklist – project file
CCA assembly drawing
  (E release until built – EO release prior to qual)
BOM –
  (E release until built – EO release prior to qual)
Analysis (initial / final after qual) – Sensitivity and Derating, project memo
Test Procedure (E release)
CDR review package – as required
ADVT CDR checklist
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 32: Preliminary design – Digital Work package
Requirements
Box Requirement - HRD
CCA Requirement – HRD
Design Documentation
Preliminary design data & doc’s
Risk mitigation test results
Plans
DTC targets and DFMAT plans
Guidelines & Checklists
High Voltage Control Plan
Program IMS & ETCs
Inputs
Tasks
Deliverables
Detailed Design – PDVT WP17
Resources :
- PDVT (1880)
- Components ( 120 )
- PWB design ( 360)
- PACT (60)
- EE Tech ( 120)
Design trade study – if needed, project memo
Estimate - Area, power if needed, project memo
Block diagram (Card), MRE document (EO release)
Requirement CCA card HRD – if needed
  (EO release) REV Doors – clear case
Schematic Peer Review – project memo – results of review with SME
Schematic checklist
  error report completed and resolved – team center
Schematic (E release until built – EO release prior to qual)
  data base in team center
Board layout guidelines for each CCA, (EDP) – team center
Board layout Peer Review, part placement and trace routing checklist – project file
CCA assembly drawing (E release until built – EO release prior to qual)
BOM – (E release until built – EO release prior to qual)
Analysis (initial / final after qual) – Sensitivity and Derating, project memo
Test Procedure (E release)
CDR review package – as required
2D & 3D HV Analysis Report – (E-Release)
PDVT CDR Checklist
Requirements
Finalize block diagram (80)
Update CCA HRD (120)
Design
Finalize schematic (240)
Magnetic design (360)
Generate EDP (40)
Perform board layout / trace route (360)
Analysis
Finalize Design Analysis, Stress, Loop Stability (320)
Support Reliability / FMEA analysis (40)
Generate requirement to design compliance matrix (160)
2D&3D HV analysis (HV) (120/60)
Components
Finalize BOM, DTC and Obsolescence (80)
Generate library models as needed (40)
Test
Finalize prototype risk testing (120)
Reviews / Reports
Schematic, layout and tracing routing review (80)
Update DMFAT compliance report (40)
Prepare CDR package (60)
Generate SDRL documents (60)
Prepare design doc – HDD (160)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 33
Inputs
Tasks
Deliverables
Detailed Design – PACT WP18
Resources
- PACT (1092)
Requirements
Support Detail ICD – Box / CCA pin-outs, I/O
specification, interconnect definition (8)
Design
Detail packaging design (240)
Analysis
Finalize board level thermal, structural,
mechanical tolerance, clearance analysis (80)
Finalize Box level thermal, structural, mechanical
tolerance, 2D&3D clearance sup’t (360)
Components / Drawings
Finalize MBS BOM, Part, cable, assembly &
installation dwgs (160)
Support library models as needed (connectors, etc) (24)
Test
Complete risk reduction testing (80)
Reviews / Reports
Detail power / area / weight estimates (80)
Peer Reviews with SME’s (20)
CDR preparation (40)
Requirements
Mission Profiles
High voltage control plan
Updated HRD and CCA HRDs
Design Documentation
Preliminary design data & documentation
Risk Mitigation test results
Plans
Updated DTC and DFMAT
Updated Program IMS & ETCs
Guidelines & Checklists
Design trade study – if needed
  project memo
Box - Top Level Assembly Drawing
  E release until built – EO release prior to qual
  data base in team center
Box - Drawing (3 D exploded view – PDF format
  models and drawings in team center
Box - Installation Drawing
  E release until built – EO release after customer approval
  data base in team center
Box - Drawing - torque definitions
  data base in team center
Box - Detailed Size/volume, weight report
  memo or power point
Box - Peer Review –– results of review with SME
  project memo, project file
Box - Packaging check list / standards
  project file
Analysis (initial / final after qual) – Thermal /
Vib / Mech Tol report project file
CDR review package – as required
PACT CDR Checklist
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 34: Qual Test Work Package
Requirement Updates
Torque-Speed-Power
Rtt/Ltt, Kt/Ke,
Inertia, peak acceleration
Min/Max Voltage/Current
Commutation/Sensor Type
Cable length, Environmental
DTC targets and DFMAT plans
Design Documentation
Design data and analysis
Prototype test results
Plans
DTC, DFMAT
Prototype Motor Test Results – Project Memo
Detailed Installation Drawings (EO)
Detailed Interface Control Documents (EO)
Detailed Design Drawings (Team Center)
Detailed Part Lists (BOM’s) (Team Center)
Detailed 3-D Envelope Model (Team Center)
Detailed Weights – Project Memo
Detailed Performance Analysis – Project Memo
DTC Analysis summary – Project Memo
MDVT CDR checklist
Inputs
Tasks / ETC
Deliverables
Resources (848)
- Motor design ( 584 hrs)
Drafting (164 hrs)
Technician (100 hrs)
Detail Design – MDVT WP19
Requirements
Requirement updates (40)
Design
Detailed Assembly Design/Modeling (60/16)
Design to Cost (DTC) Analysis/Monitoring (40)
Analysis
Finalize weight estimates (20)
Finalize Component Sizing (20)
Finalize Component Design Modeling (40)
Finalize Design & Performance Analysis (180)
Finalize definition of High Voltage Manufacturing processes (24)
Components / Drawings
EO Release Drawings (20/20)
Drawing Reviews/Approvals (20/40)
Detailed Installation Drawing (16/8)
Detailed Component Drawings (40/60)
Test
Performance verification prototype motor (24/100)
A & T Worksheet Reviews/Approvals (20)
Risk Mitigation including HV & Report (20)
Reviews / Reports
CDR Preparation and Follow-up Actions & CDR (40/20)
Return to summary page
Return to swimlane
Revised: January 21, 2014
Notes: 34

## Slide 35: Phase 4 Exit Criteria
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 36: Phase 4 Exit Criteria
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 37: Phase 5 – Item Build and Test Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 38: Qual Test Work Package
Inputs
Tasks / ETC
Deliverables
Resources (hrs)
- IDVT (1840)
Item Build and Test – IDVT WP21
Design Data
CCA Gerber files
Box Req’t & Design Doc – HRD & HDD
Board req’t & Design Doc - CCA HRD & HDD
FW Req’t & Design Doc - FDD & FRD
PLD Code
Released Schem’s, BOM, CCA & box Assy’s
Plans
EMCP (Electronics Manu Control Plan)
Program IMS&ETC
DTC target/actuals and DFMAT plans
Risk mitigation plan
Hardware/other
Assembled CCAs, & Chassis
CCA/Box Devel Test equipment & Test SW
ATP SW & EMC SW
CCA/Box Development test plan
Lab equip for test and troubleshooting
Document Box ATP / Preliminary Limits
  (E release with box test software)
Document Test results
  project file - data spread sheet or memo
Document Test coverage and test limits
  project file
Document SOF ATP
  (E release)
Box / System SOF EMC test procedure
  (E release)
HALT / HASS procedure – if required
  (E Release)
PQ procedure (E Release)
ROF procedure (E Release)
Build
Box build / procurement activities (100)
Documents
Box compliance and verification matrix (240)
Box test procedure – ATP and ATP limits (240)
SOF Box test procedure – SOF ATP (120)
PQ (power quality) and ROF (Risk of fire) procedures (40)
HALT / HASS procedure (80)
BOX / System EMC test procedure (120)
Generate design changes and rework instructions (40)
Create PR for requirement changes (60)
Test
Box HW integration of CCA’s (240)
Box ATP (120)
HALT and HASS testing (160)
Box integration into the high level system (80)
Risk mitigation testing, EMC, Temp, Vib, ALT,
humidity, water, Icing (160)
Reviews / Reports
Support SOI#2 (40)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 39: Qual Test Work Package
Inputs
Tasks / ETC
Deliverables
Item Build and Test – DDVT WP22
Resources :
- DDVT (600 hrs)
- Components (10 hrs )
- PWB design (10 hrs)
- EE Tech (80 hrs)
Design Data
CCA Gerber files
Box Req’t & Design Doc – HRD & HDD
Board req’t & Design Doc - CCA HRD &HDD
Released Schem’s, BOM, CCA & box Assy’s
PLD code
Plans
Program IMS & ETCs
CCA DTC target/actuals and DFMAT plans
Test concept / Risk mitigation plan
Hardware
Assembled CCAs
CCA/Box Devel Test equipment & Test SW
CCA/Box Development test plan
Lab equipment for test and troubleshooting
1. Document Test results
  project file - spread sheet or memo
2. Document Test coverage and test limits
  project file
3. Risk Mitigation test report – if needed
project memo
4. Successful completion of SOI #2
  audit summary in clear case
5. Board test procedure document
  E Release
6. PLD design – PLD source code, E release
7. Functional test benches
  updated and captured in Clear Case
8. Functional PLD simulation / post route results captured in project file/clear case
Build
Support CCA procurement and build activities
(40/5/10)
Documents
Develop CCA test procedure (80/20)
Generate design changes, support generation of
rework instructions, retest, & update the design
drawings (80/5/10/10)
CCA test coverage analysis as appropriate (80)
Test and Integrate
Test CCA, document results and update test
procedure as required (120)
Perform robustness (environmental, voltage,
frequency, etc) tests as appropriate (80/40)
Risk testing prior to formal qual (40)
Support integration of CCA into Box (80)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 40: Qual Test Work Package
Procedure/Test Bench
Update test procedures/test benches, as required (200)
Analysis/Simulation
Perform code simulation (min/max/typ) (160)
Perform elemental analysis (160)
Reviews
Update requirement checklists (40)
Complete HVTCP/HVR checklist (80)
Peer review of test results & simulations [HVR] (120)
Prepare for SOI#2 (80)
PLD Test
Perform Do254 V & V tests (prototype testing used for
credit), document results (360)
Documentation
Update compliance matrix with test results (40)
Create and resolve PR (80)
Inputs
Tasks / ETC
Deliverables
Resources (hrs)
- DDVT (1560)
Item Build and Test – FW V&V WP23
Requirements
Box Req’t & Design Doc – HRD & HDD
Board req’t & Design Doc - CCA HRD & HDD
FW Req’t & Design Doc - FDD & FRD
Design Documentation
PLD Code
Released Schem’s, BOM, CCA & box Assy’s
CCA Gerber files
Hardware
Assembled CCAs, & Chassis
CCA/Box Devel Test equipment & Test SW
CCA/Box Development test plan
Lab equipment for test and troubleshooting
Plans
Program IMS & ETCs
PHAC
HVP
HVTP
Successful completion of SOI #2
  audit summary in clear case
PLD design – PLD source code tracing
  Stored in Clear Case/DOORS
Functional/Verification test benches
  updated -captured in Clear Case
Functional PLD and Post Route simulation
  results captured in project file
  And captured in Clear Case
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 41: Qual Test Work Package
Build
Support CCA build / procurement activities (40/5/10)
Documents
Develop CCA test procedure (60/10)
Generate design changes, support generation of rework instructions,
retest, & update the design drawings (80/5/10/10)
CCA test coverage analysis as appropriate (60)
Integrate/Test
Test CCA, document results and update test procedure as required (80)
Perform robustness (environmental, voltage, frequency, etc) tests
as appropriate (80/40)
Risk Testing prior to formal qual (40)
Support CCA integration into Box (40)
Inputs
Tasks / ETC
Deliverables
Item Build and Test – ADVT WP24
Design Data
CCA Gerber files
Box Req’t & Design Doc – HRD & HDD
Board req’t & Design Doc - CCA HRD &HDD
Released Schem’s, BOM, CCA & box Assy’s
Hardware
Assembled CCAs
CCA/Box Devel Test equipment & Test SW
CCA/Box Development test plan
Lab equipment for test and troubleshooting
Plans
Program IMS & ETCs
CCA DTC target/actuals and DFMAT plans
CCA test concept / Risk mitigation plan
Resources :
- ADVT (440 hrs)
- Components (10 hrs )
- PWB design (10 hrs)
- EE Tech (70 hrs)
Document Test results
  project file -spread sheet or memo
Document Test coverage and test limits
  project file
Risk Mitigation test report – if needed
  project memo
Board test procedure document
  (E Release)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 42: Qual Test Work Package
Inputs
Tasks / ETC
Deliverables
Item Build and Test – PDVT WP25
Resources :
- PDVT (760 hrs)
- Components (10 hrs )
- PWB design (10 hrs)
- EE Tech (350 hrs)
Build
Support CCA build / procurement activities (40/5/10)
Documents
Develop CCA test procedure (60/10)
Generate design changes, support generation of rework instructions,
retest, & update the design drawings (80/5/10/10)
CCA test coverage analysis as appropriate (60)
Test and Integrate
Test CCA (120/80)
Document CCA test results
Update test procedure as required (80)
Perform robustness / risk mitigation testing as appropriate (80/40
(environmental, voltage, frequency, etc.)
CCA Integration into Box (40)
Perform PWB, CCA, Component, Assy, & Box Level HV altitude
tests (200/200)
Design Data
CCA Gerber files
Box Req’t & Design Doc – HRD & HDD
Board req’t & Design Doc - CCA HRD &HDD
Released Schem’s, BOM, CCA & box Assy’s
Plans
Program IMS & ETCs
CCA DTC target/actuals and DFMAT plans
Test concept / Risk mitigation plan
Hardware
Assembled CCAs
CCA/Box Devel Test equipment & Test SW
CCA/Box Development test plan
Lab equipment for test & troubleshooting
Document Test results project file –
spread sheet or memo
Document Test coverage and test limits
  project file
Risk Mitigation test report – if needed
  project memo
Board test procedure document
  (E Release)
HV Altitude test reports (E Release)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 43: Qual Test Work Package
Build
Support Box build / procurement activities (40)
Perform fit check (40/40)
Documents
Generate design changes (24)
Generate design changes, support generation of rework instructions,
retest, & update the design drawings (80/10)
Create PR for requirement changes that require design modification
and resolve (20)
Update DFMAT Document (40)
Test and Integrate
Support risk mitigation test including thermal, vibration, Fit Check,
weight, Sealing, etc…as appropriate (80)
Inputs
Tasks / ETC
Deliverables
Resources (hrs)
PACT (344)
EE Tech (50 hrs)
Item Build and Test – PACT WP26
Design Data
Box Req’t & Design Doc – HRD & HDD
Assembled CCAs, & Chassis
Plans
Risk mitigation plan
Box DTC Target/actuals
Program IMS & ETCs
Hardware
Assembled Box
Fit check – Project Memo
Thermal survey – Project Memo
Initial vibe – Project Memo
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 44: Qual Test Work Package
Build
Support MRB Activity (30/20)
Support Fabrication Process (50/10)
Support Fabrication of Hardware (50/10/20)
Documents
Design to Cost (DTC) Analysis/Monitoring (20)
Document test results (10/20)
Develop Motor ATP if required (40)
Test / Integration
Perform Motor testing (10/40)
Perform Risk Mitigation testing (10/40)
Perform Motor Environmental testing if required (10/40)
Design Data
Detailed Installation Drawings
Detailed Interface Control Docs
Detailed 3-D Envelope Model
Detailed Performance Analysis
Detailed Design Drawings
Detailed Part Lists (BOM’s)
Plans
Risk mitigation plan
Box DTC Target/actuals
Program IMS & ETCs
Hardware
Assembled Motor
Inputs
Tasks / ETC
Deliverables
Resources (hrs)
- Motor design (230 hrs)
Drafting (40 hrs)
Technician (160 hrs)
Item Build and Test – MDVT WP27
Motor ATP if required (E Release)
DTC Actuals – Project Memo
Test Results – Project Memo
Return to summary page
Return to swimlane
Revised: January 21, 2014
Notes: 44

## Slide 45: Phase 5 Exit Criteria
Revised: January 21, 2014

## Slide 46: Phase 5 Exit Criteria
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 47: Phase 6 – System Integration and SOF Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 48
Inputs
Tasks / ETC
Deliverables
System Integration and SOF – EMC/SOF Test Support [IDVT] WP29
Resources (hrs)
- IDVT (600)
Design Documentation
Test Procedures, including EMC Test Procedure
Problem reports from previous Phase
DFMAT Document
Hardware
Hardware from System/Mechanical for SOF & EMC Tests
Test Equipment and Test SW
from System Test and SW groups
SOF CCA/Box Build Hardware
Integrated Box from Build & Test
Problem reports under configuration control
  clear quest
Updated ATP /Limits Justification – as required
  EO release - REV
SOF EMC test procedure
  EO release
SOF EMC Test report
  SDRL
SOF Environmental qual test procedure
  EO release
SOF Environmental qual test report
  SDRL
DFx (M,A,T) at Box level report
  project memo
Updated HRD, EO release new REV
Test
Perform box integration testing
Perform SOF testing
Reviews
Lead SOF readiness reviews
Create and Maintain problem reports
Evaluate rest results vs requirements
Support Box conformity – if needed
Documents
Update ATP – as needed
Support completion of QTP
Update DFMAT
Update HRD, as required (40)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 49
Inputs
Tasks / ETC
Deliverables
System Integration and SOF – Design Turn [DDVT] WP30
Resources (hrs)
- DDVT (480)
Problem reports under configuration ctrl
  clear quest
Updated CCA schematic – as required
  – EO release for qual
Update CCA BOM – as required
  – EO release for qual
Update CCA Assembly Drawing – as required
  – EO release for qual
Updated HRD & FRD EO release new REV
DFx (M,A,T) at Box level report
  review project memo with MFG WP
PLD Design –PLD Source code
  EO released / clear case
8. PLD FCI – EO Release
Test
Support SOF testing as required
Reviews
Support System review and validation of changes (60)
Support peer review of test results
Hold CCA PRR (60)
Documents
Create, update and resolve Problem reports (120)
Update design documentation:
schematics, BOM, timing analysis, simulation, derating,
updated requirements (120)
Update CCA Test Procedure, as necessary (40)
Update FRD, as required (40)
Update HRD, as required (40)
Generate PLD Programming Files (FCI) (40)
Requirements
Design requirements updates causing Design turns in CCAs
Design Documentation
Updated Hardware Allocation from System Hardware
SOF CCA Build Hardware
Integrated Box from Build & Test
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 50
Inputs
Tasks / ETC
Deliverables
System Integration and SOF – Design Turn [FW V&V] WP31
Resources (hrs)
- DDVT (640)
Test Procedures
Update HVTCP & Test Benches, as needed (40)
Reviews
Create and Maintain Problem reports (60)
Review elemental analysis vs source code (40)
Review code tracing – prepare checklist (200)
Review simulation results (40)
Analysis
Finalize elemental analysis (80)
Perform code post route simulation (80)
Test
Perform PLD tests, document results (80)
Establish verification environment (20)
Perform TRR prior to formal run for score (20)
Documentation
Prepare problem reports (40)
Update FW programming procedure, as necessary (40)
Problem reports under configuration control
  clear quest
PLD Design – PLD source code
  EO released
  Clear case
Code review and tracing checklist
  Clear case
Functional PLD and post route simulation results
  captured in project file
PLD Elemental Analysis Report
FW V&V TRR Checklist
Updated FRD,TB & Test Cases developed
  update through cert phase - clear case
Requirements
Design requirements updates causing Design turns in CCAs
Design Documentation
Updated Hardware Allocation from System Hardware
SOF CCA Build Hardware
Integrated Box from Build & Test
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 51
Inputs
Tasks / ETC
Deliverables
System Integration and SOF – Design Turn [ADVT] WP32
Resources (hrs)
- ADVT (440)
Requirements
Design requirements updates causing Design turns in CCAs
Design Documentation
Updated Hardware Allocation from System Hardware
SOF CCA Build Hardware
Integrated Box from Build & Test
Test
Support SOF testing as required
Reviews
Support System review and validation of changes (60)
Support peer review of test results
Hold CCA PRR (60)
Documents
Create, update and resolve Problem reports (120)
Update design documentation:
schematics, BOM, analysis, simulation, derating,
updated requirements (120)
Update CCA Test Procedure, as necessary (40)
Update HRD, as required (40)
Problem reports under configuration control
  clear quest
Updated CCA schematic – as required
  – EO release for qual
Update CCA BOM – as required
  – EO release for qual
Update CCA Assembly Drawing – as required
  – EO release for qual
DFx (M,A,T) at Box level report
  review project memo with MFG WP
Updated HRD, EO release new REV
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 52
Inputs
Tasks / ETC
Deliverables
System Integration and SOF – Design Turn [PDVT] WP33
Resources (hrs)
PDVT (520)
PACT (40)
EE Tech (40)
Problem reports under configuration
control clear quest
Updated CCA schematic – as required
  – EO release for qual
Update CCA BOM – as required
  – EO release for qual
Update CCA Assembly Drawing – as required
  – EO release for qual
DFx (M,A,T) at Box level report
  review project memo with MFG WP
Updated HRD, EO release new REV
Updated 2D & 3D HV analyses – as required (E Release)
Updated HV Altitude test reports – as required (E Release)
Requirements
Design requirements updates causing Design turns in CCAs
Design Documentation
Updated Hardware Allocation from System Hardware
SOF CCA Build Hardware
Integrated Box from Build & Test
Test
Support SOF testing as required
Reviews
Support System review and validation of changes (60)
Support peer review of test results
Hold CCA PRR (60)
Documents
Create, update and resolve Problem reports (120)
Update design documentation:
schematics, BOM, stability and transient analysis, derating,
updated requirements (120)
Update CCA Test Procedure, as necessary (40)
Update HRD, as required (40)
Update 2D & 3D HV analysis (40/40)
Update PWB, CCA, Component, Assy, & Box Level HV altitude tests
(40/40)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 53
Inputs
Tasks / ETC
Deliverables
System Integration and SOF – Design Turn [PACT] WP34
Resources (hrs)
- PACT (360)
SOF Environmental qual test report
  Support SDRL
DFx (M,A,T) at Box level report
  review project memo with MFG WP
Requirements
SOF environmental test procedure
Design requirements updates
Design Documentation
Test data from previous phase
Design changes from previous phase
Hardware
Integrated Box from Build & Test
Test
Support SOF testing as required
Reviews
Support System review and validation of changes (60)
Support peer review of test results
Support Chassis PRR (60)
Documents
Create, update and resolve Problem reports (120)
Update design documentation:
chassis drawing, update thermal and vib analysis
updated requirements (120)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 54
Inputs
Tasks / ETC
Deliverables
System Integration and SOF – Design Turn [MDVT] WP35
Resources (hrs)
- MDVT (320)
Problem reports under configuration control clear quest
Updated Motor Req’ts Doc
Updated Motor ATP (EO)
Updated Motor documentation (EO)
Production Readiness Review complete
Test
Support Motor/Actuator SOF testing (10)
Reviews
Support SOF readiness review (4)
Hold Motor PRR (40)
Evaluate design requirements updates (24)
Support System validation of changes (32)
Documentation
Create and Maintain Problem reports (16)
Update Motor design documentation (8)
Update Motor requirements as needed (4)
Update Motor ATP, as necessary (40)
Requirements
SOF environmental test procedure
Design requirements updates for Motor
Design Documentation
Test data from previous phase
Design changes from previous phase
Hardware
SOF Motor Build
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 55: Phase 6 Exit Criteria
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 56: Phase 6 Exit Criteria
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 57: Phase 7 – Qualification Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 58
Inputs
Tasks / ETC
Deliverables
Qualification Phase – System EMC/Qual [IDVT] WP37
Resources (hrs)
- IDVT (880)
Requirements
ATP
QTP
Design Documentation
SOF results / modifications
Hardware
Qualification HW
Qualification SW (as required)
Test Equipment / test cables
Procedures
Prepare/review EMC and Environmental test procedures (200)
Schedule test labs(40)
Update ATP, as needed (40)
Update compliance (verification) trace matrix (80)
Reviews
Coordinate/Support review and insure test setup is ready (40)
Prepare readiness review checklist(20)
Create and Maintain problem reports
Test
Support EMC and Environmental testing (40)
Power Quality testing (40)
Evaluate Qual test results (40)
Support / Document Design modifications as needed(40)
Test Reports
Prepare Environmental & EMC test reports(160)
Review and approve qualification test reports (40)
Submit reports for review/signoff(20)
Problem Reports
Create and Maintain Problem reports as needed (40)
Conduct Box PR (40)
Problem reports configured –
clear quest
EMC Qualification test procedure –
EO released
EMC Qualification Test Report - SDRL
Environmental Qualification Test Procedure - EO released
Environmental Qualification Test Report - SDRL
Power Quality Test Report as required SDRL
LRU requirements update- Doors update - REV
Updated ATP - EO Released - REV
Verification Trace Matrix evidence in Doors or spreadsheet
DFx(M,A,T) at Box level summary memo MFG WP
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 59: Qual Test Work Package
Test Procedures
Finalize test Cases, as required (40)
Finalize test benches, as required (40)
Analysis/Simulation (run for score)
Perform Verification Simulation (120)
Review results (40)
Complete review checklists (40)
Documentation
Finalize HVR (40)
Finalize HW compliance matrices (40)
Review
Complete SOI #3 review (Int & Ext) (120)
Requirements
Test Procedures released
Design Documentation
All docs under CM Control
T/E under CM Control
Hardware
Qual HW and V&V HW
Inputs
Tasks / ETC
Deliverables
Resources (Hrs)
- DDVT (500)
Qualification Phase - FW VnV Work Package WP38
Problem reports configured
  clear quest
Verification Trace Matrix
  evidence in Doors or spread sheet
SOI #3 review report
  audit in clear case
4.HVTCP/HVR Release (EO)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 60
Inputs
Tasks / ETC
Deliverables
Qualification – Qual Support [MDVT] WP39
Resources (hrs)
- MDVT (340)
Requirements
Updated Motor Req’ts Doc
Updated ATP (EO)
Design Documentation
Problem reports under configuration
Updated Motor documentation (EO)
Production Readiness Review complete
Documentation
Update ATP Motor/Actuator, as needed (Actuator support only) (40)
Update Motor Req’ts Doc (40)
Update Motor documentation (80)
Update compliance matrix (16)
Reviews
Conduct Motor PRR (40)
Prepare readiness review checklist(20)
Test
Support System Qualification Testing (40)
Evaluate Qualification test results and feedback design change requirements to Motors and/or Drive electronics (60)
Problem Reports
Create and resolve Problem reports (40)
Resolved Problem reports
Updated ATP Motor/Actuator, as needed (Actuator support only
Update Motor Req’s Doc
Updated Motor Documentation (EO)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 61: Phase 7 Exit Criteria
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 62: Phase 8 – Certification Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 63
Inputs
Tasks / ETC
Deliverables
Certification Phase – Design Turn [IDVT] WP41
Resources (hrs)
- DDVT (440)
Procedures
Prepare Environmental test procedure (40)
Schedule test lab (40)
Prepare EMI test procedure (40)
Schedule test lab (40)
QBS (Qual By Similarity) reports as required (40)
Review
Coordinate / support readiness review (40)
Prepare readiness review checklist (40)
Create and Maintain problem reports
Test Report
Prepare Environmental test report (40)
Submit report for review / signoff (40)
Prepare EMI test report (40)
Submit report for review / signoff (40)
Problem Reports
V+V actions / issues
Blue / Red label problem list
Qualification Data
Environmental test issues
EMI test issues
DFX Inputs
Manufacturability DFX inputs
DTC updates
Requirements
CCA design requirements updates
Problem reports closed or deferred – clear quest
Successful transition of design to production evidence that PRR Checklist is complete and actions are closed (Project Memo)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 64
Requirements
Update requirements / block diagrams – as required (40)
Update compliance matrix / HVR (40)
Design Changes
Evaluate design and manufacturability DFX inputs (40)
Evaluate Qual changes and incorporate (40)
Update Schematic / BOM (40)
Update Analysis (performance / Timing / Simulation) (40)
Update part placement and trace routing instructions (40)
Update design documentation / description (40)
Update CCA Test Procedure, as necessary (40)
PWB Updates
Review part placement changes (40)
Review trace routing changes (40)
Problem Reports
Close out all PRR actions (40)
Production
Support production Hardware Build / readiness review (40)
Inputs
Tasks / ETC
Deliverables
Certification Phase – Design Turn [DDVT] WP42
Resources (hrs)
- ADVT (520)
Problem Reports
V+V actions / issues
Blue / Red label problem list
Qualification Data
Environmental test issues
EMI test issues
DFX Inputs
Manufacturability DFX inputs
DTC updates
Requirements
CCA design requirements updates
Problem reports closed or deferred - clear quest
HW accomplishments summary (EO)
Successful SOI #4 review audit report in clear case
Updated CCA Drawing Package, EO release
  Schematic
  BOM
  Assembly Drawing
Updated CCA Test Procedure
Updated Analysis, Project Memo
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 65
Inputs
Tasks / ETC
Deliverables
Certification Phase – Design Turn [ADVT] WP43
Resources (hrs)
- ADVT (560)
Problem Reports
V+V actions / issues
Blue / Red label problem list
Qualification Data
Environmental test issues
EMI test issues
DFX Inputs
Manufacturability DFX inputs
DTC updates
Requirements
CCA design requirements updates
Requirements
Update requirements – as required (40)
Update compliance matrix / HVR (40)
Design Changes
Evaluate design and manufacturability DFX inputs (40)
Evaluate Qual changes and incorporate (40)
Update Schematic / BOM (40)
Update Analysis (performance / Stress) (40)
Update part placement and trace routing instructions (40)
Update design documentation / description (40)
Update CCA Test Procedure, as necessary (40)
Peer Review changes (40)
PWB Updates
Review part placement changes (40)
Review trace routing changes (40)
Problem Reports
Close out all PRR actions (40)
Production
Support production Hardware Build / readiness review (40)
Updated CCA Drawing Package, EO release
  Schematic
  BOM
  Assembly Drawing
Updated CCA Test Procedure
Updated Analysis, Project Memo
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 66
Inputs
Tasks / ETC
Deliverables
Certification Phase – Design Turn [PDVT] WP44
Resources (hrs)
PDVT (680)
PACT (40)
EE Tech (40)
Problem Reports
V+V actions / issues
Blue / Red label problem list
Power Quality Inputs
Qualification Data
Environmental test issues
EMI test issues
DFX Inputs
Manufacturability DFX inputs
DTC updates
Requirements
CCA design requirements updates
Requirements
Update requirements – as required (40)
Update compliance matrix / HVR (40)
Insure that CCA is compatible with Aircraft capability and has been verified. (40)
Insure power requirements compatible with SW / FW (40)
Design Changes
Evaluate design and manufacturability DFX inputs (40)
Evaluate Qual changes and incorporate (40)
Update Schematic / BOM (40)
Update Analysis (performance / Stress) (40)
Update part placement and trace routing instructions (40)
Update design documentation / description (40)
Update CCA Test Procedure, as necessary (40)
Update 2D & 3D HV analysis (40/40)
Update PWB, CCA, Component, Assy, & Box Level HV altitude tests (40/40)
PWB Updates
Review part placement changes (40)
Review trace routing changes (40)
Problem Reports
Close out all PRR actions (40)
Production
Support production Hardware Build / readiness review (40)
Updated CCA Drawing Package, EO release
  Schematic
  BOM
  Assembly Drawing
Updated CCA Test Procedure
Updated Analysis, Project Memo
Updated 2D & 3D HV analyses – as required (E Release)
Updated HV Altitude test reports - as required (E Release)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 67
Inputs
Tasks / ETC
Deliverables
Certification Phase – Design Turn [FW V&V] WP45
Resources (hrs)
- DDVT (360)
Requirements
Design requirements updates causing Design turns in FW
Hardware
Qual CCA Build Hardware
Qual Firmware
Integrated Box from Qual
Documentation
Prepare HAS (160)
Review HAS and complete checklist (60)
Problem Reports
Review and Update Problem reports (60)
Audits
Support SOI #4 review (80)
Problem reports Closed or Deferred
  clear quest
HW accomplishment summary
  EO Release
Successful SOI #4 review
  audit report in clear case
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 68
Inputs
Tasks / ETC
Deliverables
Certification Phase – Design Turn [PACT] WP46
Resources (hrs)
- PACT (360)
Hardware
Qual CCA Build Hardware
Integrated Box from Qual
DFX Inputs
Manufacturability inputs for final design spin
Requirements
Design requirements updates causing Design turns
Design Changes
Evaluate design and manufacturability requirements updates for best implementation in hardware (40)
Update design documentation: drawings, BOM, analysis, simulation, etc… for updated requirements (120)
Support System validation of changes (40)
Problem Reports
Create and Maintain Problem reports (40)
Production
Closeout Box PRR actions (40)
Update Box ATP, as necessary (40)
Support initial production Hardware Build (40)
Updated Drawings & Models, EO release
  BOM
  Assembly Drawing
  Chassis
  Mechanical Subassemblies
Updated Analysis, Project Memo
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 69
Inputs
Tasks / ETC
Deliverables
Certification – Qual Support [MDVT] WP47
Resources (hrs)
- MDVT (340)
Problem Reports
Problem reports under configuration
DFX Inputs
Production Readiness Review complete
Requirements
Updated Motor Req’ts Doc
Updated ATP (EO)
Updated Motor documentation (EO)
Test
Support System Qualification Testing (40)
Design Changes
Update Motor Req’ts Doc (40)
Update Motor documentation (80)
Evaluate Qualification test results and feedback design change requirements to Motors and/or Drive electronics (60)
Update ATP Motor/Actuator, as needed (Actuator support only) (40)
Problem Reports
Create and resolve Problem reports (40)
Production
Conduct Motor PRR (40)
Resolved Problem reports
Updated ATP Motor/Actuator, as needed (Actuator support only)
Motor PRR Complete
Updated Motor Req’ts Doc
Updated Motor documentation (EO)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 70: Phase 8 Exit Criteria
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 71: Product Maturation/EIS and Sustainment Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 72
Inputs
Tasks / ETC
Deliverables
Design Engineering – Product Maturation/EIS (FPY > 92%) WP49
Resources (hrs)
- Project/IDVT (100% LOE)
Manufacturing Data
FPY (supply chain, CCA, Box)
Product cost data
NC history
RURs
Parametric ATP Data
Supplier quality rating
Supply chain sourcing strategies
Program/Design Data
Customer demands (design change, new features, etc)
Obsolescence Status, Errata
Fielded MTBUR, DMC
Refresh Strategy
Support Weekly Manufacturing-Design meetings
Updated drawings, BOMs, ATP, HASS, ATP Limits, etc as required
Delta Qual documents as required
Lead Tasks
Conduct EIS Review (entry event when FPY > 92%)
Program Reviews (Moog with Moog customers)
Lead RCCAs as required.
Develop solutions to design problems
Actively work to reduce NCs and improve FPY
Review ATP Limits with respect to FPY, NCs and parametric data and
make changes as appropriate
Lead Cost/Product/Process improvement initiatives as required
Lead Delta Qualification/Certification, QBS, etc activities as required
Create and Maintain problem reports
Support Tasks
CRB Support
Drawing, BOM, ATP, HASS, etc updates as required
Review supplier performance data as required
Support Reliability Testing activities (i.e. ongoing Proof of HASS, etc)
Support Supply Chain transitions as required
Review Parametric test data for shifts and out of family trends
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 73
Inputs
Tasks / ETC
Deliverables
Design Engineering – Sustainment (FPY > 99%) WP51
Resources (hrs)
- Project/IDVT (25% LOE)
Manufacturing Data
FPY (supply chain, CCA, Box)
Product cost data
NC history
RURs
Parametric ATP Data
Supplier quality rating
Supply chain sourcing strategies
Program/Design Data
Customer demands (design change, new features, etc)
Obsolescence Status, Errata
Fielded MTBUR, DMC
Refresh Strategy
Support Weekly Manufacturing-Design meetings
Updated drawings, BOMs, ATP, HASS, ATP Limits, etc as required
Delta Qual documents as required
Support Tasks
CRB Support
Program Reviews (Moog with Moog customers)
Support RCCAs as required
Develop Refresh Strategy working with Program team, customer and
manufacturing engineering
Cost/Product/Process improvement initiatives as required
Drawing, BOM, ATP, HASS, etc updates as required
Delta Qualification/Certification, QBS, etc activities as required
Support Reliability Testing activities (i.e. ongoing Proof of HASS, etc)
Support Supply Chain transitions as required
Review Parametric test data for shifts and out of family trends
Review ATP Limits with respect to FPY, NCs and parametric data and
make changes as appropriate
Create and Maintain problem reports
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 74: Phase 1 – MFG Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 75
1. DTC feedback to project team
2. EMCP1(MFG plan)
Inputs
Tasks / ETC
Deliverables
Resources (hrs)
Operations Lead (28)
Prod/Proc Engineering (32)
Supply Chain (16)
76 hours total
Requirements Definition - Mfg Project Plan WP4
Requirements
Spec/SOW
Box HRD
Proposal Baseline
DTC Targets
Schedule
Updated quantities and milestones
Plans
Quality flow down
Proposal EMCP0
Cert/Project Plan
Preliminary product structure
Project Preparation
Review Proposal Baseline including budgets (8)
Review product relative to platforms for synergy (4)
Review plan for magnetic sourcing (4)
Review plan for cable assemblies sourcing (4)
Review plan for mechanicals including box (8)
Design Requirements & Standards
Capabilities gap analysis
(capacity, equipment, processes, materials, etc) (8)
Review DTC targets versus plan/actuals (8)
Defined prototype and production build locations
Update EMCP1 (32)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 76: Phase 3 – MFG Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 77
Requirements
Preliminary CCA Design Info
Updated quantities and
milestones
Updated Box HRD
Plans
EMCP1
Revised project plan/scope changes
DFX
Revised DTC Targets
Inputs
Tasks / ETC
Deliverables
Preliminary Design – Prelim. Mfg process definition WP12
DFx (M,A,T) at Box level summary
DFx (M,A,T) at CCA level summary
Process flow diagram
DTC feedback to project team
EMCP2
Requirement Reviews
Review preliminary block diagrams /allocations (24)
Review preliminary BOM and schematics(32)
Review preliminary Box design (24)
Plans
Updated EMCP2 (32)
Review risk management plan (16)
Review DTC targets versus plan/actuals (16)
DFX
Conduct DFx (M,A,T) reviews (40)
Resources (hrs)
Operations Lead (36)
Prod/Proc Engineering (128)
Supply Chain (20)
184 hours total
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 78
Requirements
Preliminary CCA Design Info
CCA Risk Build data as required
Updated quantities and
milestones
PDR materials
Plans
EMCP2
Revised project plan/scope changes
DFX
Revised DTC targets
Inputs
Tasks / ETC
Deliverables
Preliminary Design – Prototype/Risk Mitigation Build
Requirement Reviews
Review preliminary design box and CCA (80)
Plans
Updated and released EMCP3 (24)
Refine AWs, TWs if required to support product and
process engineering per EMCP (180)
DFX
Review DTC targets versus plan/actuals (16)
Conduct DFx (M,A,T) reviews (80)
DFx (M,A,T) at Box level summary
DFx (M,A,T) at CCA level summary
AWs and TWs if required
Prototype/risk mitigation CCAs, as required
Product/Process/Ops PDR materials
DTC feedback to project team
EMCP3
Resources (hrs)
Operations Lead (24)
Prod/Proc Engineering (340)
Supply Chain (16)
380 hours total
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 79: Phase 4 – MFG Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 80
Project
Revised project plan
/ scope changes
Plans
EMCP3
Latest AW, TW
Requirements
CCA TRDs
Detailed Design Package
Revised DTC Targets
Special test Reqs (HASS, etc)
Inputs
Tasks / ETC
Deliverables
Detailed Design - Mfg Process definition WP20
Design Support / Reviews
Review detailed drawings box and CCA (120)
Review DTC targets versus plan/actuals (32)
Review TRD (Test Requirement Docs) (32)
Drawings
Update EMCP4 (24)
Refine AW with CEM Process Engineering (160)
Refine TW with CEM Product Engineering (160)
Production
Visit CCA CEM and audit per strategy (300)
Resources (hrs)
Operations Lead (40)
Prod/Proc Engineering (748)
Supply Chain (40)
828 hours total
MFG - DFMAT – Peer review with MFG
  project memo / action resolution
MFG - EMCP4 (MFG plan update)
CDR review package – as required
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 81: Phase 5 – MFG Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 82
Design Data/Requirements
CCA Dev Test Procedure
Released PLD code
Box ATP test requirements
Box ATP limits justification
Box ATP
Plans
EMCP4
Revised project plan/scope changes
Latest AW, TW
Revised DTC Targets
Hardware/other
POB hardware, tooling
CCA Dev Test Fixtures
Inputs
Tasks / ETC
Deliverables
Item Build & Test – Dev HW Build CCA/Item WP28
DFx (M,A,T) at Box level summary
DFx (M,A,T) at CCA level summary
Hardware CCA (turn0), QTY based on project need
Hardware box (turn0), Qty based on project need
Updated AW, TW if required
Proof of build report – Project memo
DTC feedback to project team - Project memo
EMCP5
Build
Liaison with CEM (120)
Update box and CCA AWs & TWs if required (200)
Conduct POB and report (280)
Documents
Update EMCP5 (8)
Test
Support box and CCA Test Procedures as required (200)
Support Des Engineering testing (24)
Reviews / Reports
Validate DTC actuals (40)
Review DTC targets versus plan/actuals (24)
Support MRB (120)
Resources (hrs)
Operations Lead (80)
Prod/Proc Engineering (856)
Supply Chain (80)
1016 hours total
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 83: Phase 6 – MFG Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 84
Requirements
Revised project plan/scope changes
Revised DTC Targets
Design Documentation
EMCP5
Latest AW, TW
POB report from turn0 hwr
System Integration and SOF – SOF Build CCA/Item WP36
Test
Support Des Engineering testing (30)
Reviews
Support MRB (60)
Documents
Updated EMCP6 (16)
Production
Update box and CCA AWs (turn0 hardware plus cuts
and jumper) & TWs as required (80)
Liaison with CEM (160)
Review DTC targets versus plan/actuals (24)
Inputs
Tasks / ETC
Deliverables
Resources (hrs)
Operations Lead (16)
Prod/Proc Engineering (338)
Supply Chain (16)
370 hours total
SOF LRU build
  QTY based on project
DFx (M,A,T) at Box level report
  project memo
EMCP6
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 85: Phase 7 – MFG Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 86
Design Documentation
SOF design and BOM update
Assembly Drawings
Plans
Revised project plan/scope changes
Revised DTC Targets
Qualification Phase – Production Readiness Qual Builds WP40
Qualification Build
Liaison with CEM (320)
Update box and CCA AWs & TWs if required (100)
Coordinate cable builds (80)
Production Readiness Review
Support box and CCA Test Procedures as required (180)
Support DTC targets versus plan/actuals (40)
Support MRB (120)
Plans
Updated EMCP7 (16)
Reviews
DFX reviews (24)
Inputs
Tasks / ETC
Deliverables
Resources (hrs)
Operations Lead (-)
Prod/Proc Engineering (-)
Supply Chain (-)
880 hours total
Qualification LRU’s
  QTY based on project
DFx (M,A,T) at Box level summary
  memo MFG WP
EMCP7
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 87: Phase 8 – MFG Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 88
Reports
POB report from turn1 hwr
Project
Revised project plan/scope changes
DFX Inputs
Revised DTC Targets
Requirements
EMCP7
Latest AW, TW
Certification Phase – Production Hardware Build WP48
Production
Liaison with CEM (240)
Develop plan for production (120)
Develop plan for sustaining engineering (40)
Reviews
Review DTC targets versus plan/actuals (16)
Support MRB (120)
Plans
Update EMCP8 (16)
Inputs
Tasks / ETC
Deliverables
Resources (hrs)
Operations Lead (24)
Prod/Proc Engineering (512)
Supply Chain (16) -552 hours total
Successful transition of design to production
Product engineers are trained
Documentation to support build/test - released
Updated AW, TW if required MFG
EMCP8
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 89: Product Maturation/EIS and Sustainment Work Packages
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 90
Generate Incident Database
Generate parametric data summary
Lead weekly Manufacturing-Design meeting ‘Product Yield Top Concerns’
Conduct Monthly Manufacturing Review meeting with LRU team (FPY, NC, on Hold, cost, etc)
Update TW, AW as required
Manufacturing Data
FPY (supply chain, CCA, Box)
Product cost data
NC history
RURs
Parametric ATP Data
Supplier quality rating
Supply chain sourcing strategies
Program/Design Data
Customer demands (design change, new features, etc)
Obsolescence Status, Errata
Fielded MTBUR, DMC
Inputs
Tasks / ETC
Deliverables
Manufacturing Engineering – Product Maturation/EIS (FPY > 92%) WP50
Support Tasks
Develop Plan for Every Part (P4EP)
CRB support
Supplier performance review meetings
Support RCCAs as required
Create and Maintain problem reports
Process Data
Process parametric data from CCA and Box ATP
Lead test equipment maintenance and upgrade activities
Resources (hrs)
Product/Proc Eng (50%/25% LOE)
Supply Chain (25% LOE)
QE (5% LOE)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 91
Maintain Incident Database
Maintain parametric data summary
Lead weekly Manufacturing-Design meeting ‘Product Yield Top Concerns’
Conduct Monthly Manufacturing Review meeting with LRU team (FPY, NC, on Hold, cost, etc)
Update TW, AW as required
Manufacturing Data
FPY (supply chain, CCA, Box)
Product cost data
NC history
RURs
Parametric ATP Data
Supplier quality rating
Supply chain sourcing strategies
Program/Design Data
Customer demands (design change, new features, etc)
Obsolescence Status, Errata
Fielded MTBUR, DMC
Inputs
Tasks / ETC
Deliverables
Manufacturing Engineering – Sustainment (FPY > 99% WP52
Lead Tasks
Conduct Product Maturation Entry Review (entry event
when FPY > 99%)
Lead RCCAs as required
Create and Maintain problem reports
Support Tasks
CRB support
Supplier performance review meetings
Process Data
Process parametric data from CCA and Box ATP
Lead test equipment maintenance and upgrade activities
Resources (hrs)
Product/Proc Eng (25%/10% LOE)
Supply Chain (10% LOE)
QE (5% LOE)
Return to summary page
Return to swimlane
Revised: January 21, 2014

## Slide 92: Acronyms
B | 
BOM | Bill Of Materials
BLDC | Brushless Direct Current
A | 
ADVT | Analog Design Verification and Test
ATP | Acceptance Test Procedure
ALT | Altitude
AW | Assembly Worksheet
ABOM | Advanced Bill of Material
A&T | Assembly & Test
C | 
CCA | Circuit Card Assembly
CDR | Critical Design Review
CR | Change Request
CM | Configuration Management
CERT | Certification
CEM | Contract Electronics Manufacturer
D | 
DDVT | Digital Design Verification and Test
DFx (M,A,T) | Design for x where x can be Manufacturing, Cost, Assembly and Test, etc
DTC | Design To Cost
DFMAT | Design for Manufacturability, Assembly and Test
DUT | Device Under Test
DEV | Development
DMC | Direct Maintenance Cost
Return to summary page
Revised: January 21, 2014

## Slide 93: Acronyms (continued)
E | 
EE | Electrical Engineering
EMPT | Electronics Manufacturing Process and Test
EDP | Electronics Design Plan (Special Instructions used for PWB Layout definition)
EO | Engineering Order: form and procedure for implementing design changes
EMC | Electromagnetic Compliance (Compatibility)
EMI | Electromagnetic Interference
EM | Electro-Mechanical
ETC | Estimate To Complete
EVMS | Earned Value Management System
EMCP | Electronics Manufacture Control Plan
F | 
FCI | Firmware Configuration Index
FRD | Firmware Requirements Document
FW V&V | Firmware Verification and Validation
FEs | Functional Elements
FMEA | Failure Mode Effects Analysis
FDD | Firmware Design Drawing
FW | Firmware
Return to summary page
Revised: January 21, 2014

## Slide 94: Acronyms (continued)
H | 
HALT | Highly Accelerated Life Test
HAS | Hardware Accomplishment Summary
HASS | Highly Accelerated Stress Screens
HCMP | Hardware Configuration Management Plan
HDP | Hardware Development Plan
HDD | Hardware Description Document
HEPG | Hardware Engineering Process Group
HVP | Hardware Verification Plan
HRD | Hardware Requirements Document
HW | Hardware
HV | High Voltage
HVR | Hardware Verification Report
HVCP | Hardware Verification Cases and Procedures
HVS | Hardware Verification Standards
HVTCP | Hardware Verification Test Cases and Procedures
HVTP | Hardware Verification Test Procedures
HCMP | Hardware Configuration Management Plan
HPAP | Hardware Process Assurance Plan
HRS | Hardware Requirements Specification
I | 
ICD | Interface Control Diagram
IDVT | Item Design Verification Test
IP | Intellectual Property
IPT | Integrated Product Teams
IR&D | Internal Research and Development
IO | Input /Output
IMS | Integrated Master Schedule
Return to summary page
Revised: January 21, 2014

## Slide 95: Acronyms (continued)
K | 
Kt/Ke | Torque constant (Kt)/Voltage constant (Ke)
L | 
LRU | Line Replaceable Unit
M | 
MDVT | Motor Design Verification and Test
MECH | Mechanical
MOC | Means of Compliance
MBS | Moog Business System
MRB | Material Review Board
MFG | Manufacturing
ME | Mechanical Engineering
MTBUR | Mean Time Between Unscheduled Removal
P | 
PHAC | Plan for Hardware Aspects of Certification
PLD | Programmable Logic Device
PRB | Program Review Board
PACT | Packaging Design Verification and Test
PDVT | Power Design Verification and Test
PDR | Preliminary Design Review
PRR | Production Readiness Review
PN | Part Number
PWB | Printed Wire Board
PPL | Preferred Parts List
PR | Problem Report
POB | Proof of Build
PROD | Production
PROC | Procedure
Return to summary page
Revised: January 21, 2014

## Slide 96: Acronyms (continued)
Q | 
QA | Quality Assurance
QUAL | Qualification
QTP | Qualification Test Procedure
QTY | Quality
R | 
RQMT | Requirement
REV | Revision
Rtt/Ltt | Terminal to Terminal Resistance and Inductance
S | 
SOF | Safety Of Flight
SOI | State of Involvement
SDRL | Subcontractor Data Requirement List
SRR | System Requirements Review
SW | Software
STE | Standard Test Equipment
SYS | System
SME | Subject Matter Expert
SOW | Statement Of Work
SSMP | System Safety Management Plan
SPEC | Specification
Return to summary page
Revised: January 21, 2014

## Slide 97: Acronyms (continued)
V | 
V&V | Verification and Validation
VHDL | Very High-level Design Language
VIB | Vibration
W | 
WP | Work Package
WO | Work Order
WBS | Work Breakdown Structure
T | 
TRD | Test Requirements Document
TRR | Test Readiness Review
TB | Test Bench
TEMP | Temperature
TWs | Test Worksheet
TE | Test Equipment
Return to summary page
Revised: January 21, 2014